## 2018-19 Audit
| Audit Finding | Reference Update Letter 12.31.2020 | Repeat from PY | Status | Status Update | Corresponding Finding from 2020 Audit Report
1 | 2019-001 Closing Process and Control Environment | Table A 2019-001 | yes Item 2018-01 | Implemented | Implemented district monthly/year end close schedule; EdgeRock Technology contracted to design and support with implementation of monthly close (Attachment 1) | Finding 2019-001 Closing Process and Control Environment
2 | 2019-002 Capital Assets | Table A 2019-002 | yes Item 2018-02 | In progress | In progress: District is currently engeged with Oracle to design asset managment module in Peoplesoft (Go-live HR Jul 2021 & Finance by Sep 2021) (Attachment #2) | Finding 2019-002 Capital Assets (1) Finding 2019-002 Capital Assets (2)
3 | 2019-003 Internal Service Fund deficit Fund Balance | Table A 2019-003 | no | Implemented | Corrective action taken | Finding 2019-003 Internal Service Fund Deficit and Fund Balance
4 | 2019-004 Vacation Accrual | Table A 2019-004 | no | Implemented | Implemented- policy update needed: 1. Admn- policy should address employees that exceeded the cap prior to implementation 2. Policy should be implemented for non-Administrators | Finding 2019-004 Vacation Accural
5 | 2019-005 Return to Title IV Program | Table A 2019-005 | yes Item 2018-03 | In progress | Contracted with EdgeRock Technology to improve financial aid administration | Finding 2019-005 Special Tests and Provision: Return to Title IV (1)
Finding 2019-005 Special Tests and Provision: Return to Title IV (2)
6 | 2019-006 Direct Loan Reconciliation | Table A 2019-006 | no | In progress | Corrective action was taken | Finding 2019-006 Special Tests and Provision: Direct Loan Reconciliation
7 | 2019-007 Special Tests and Provisions: COD Reporting 2020-007 Internal Controls Over Federal Awards | Table A 2019-007 | yes Item 2018-04 | In progress | Plan with Edgerock to improve financial aid administration | Finding 2019-007 Common Origination and Disbursement (COD) Reporting
8 | 2019-008 444-Apprenticeship Related and Supplemental Instruction (RSI) Funds | Table A 2019-008 | yes Item 2018-05 | Implemented | Corrective action was taken | Finding 2019-008 444 Apprenticeship Related and Supplemental Instruction (RSI) Funds
9 | 2019-009 425-Residency Determination for Credit Courses | Table A 2019-009 | no | Implemented | Corrective action was taken | Finding 2019-009 425 Residency Determination for Credit Courses (1) Finding 2019-009 425 Residency Determination for Credit Courses (2)
10 | 2019-010 491- Education Protection Account Funds | Table A 2019-0010 | no | Implemented | Corrective action was taken | Finding 2019-010 Education Protection Account Funds
Corrective action was taken (Attachment #1)
Corrective action was taken

## 2019-20 Audit
| 2020 Audit Results and Corrective Action Plans | [5 empty] | Financial Aid Policies and Prcedures | **Note: The 2020 audit engagement ended in February 26, 2021; the 2021 audit kicked off in May which results in the probability for repeat findings given the limited time for any implementation of corrective action to reflect in audit pool for 2021.
| Audit Finding Report | Reference Update Letter 12.31.2020 | Auditor's Recommendation | Proposed Action | Correction Implementation | Repeat from PY | Status Update | Corresponding Finding from 2020 Audit Report
1 | 2020-004 Student Financial Assistance Cluster – Special Tests and Provisions: Enrollment and Certification Approval Report | Table B 2020-002 | Recommendation: We recommend the Colleges’ establish procedures to ensure the timely reporting of ECAR changes to the Department of Education. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to implement a process for updating Department of Education of new Financial Aid staff representatives within the 10-day requirement. | 1) Improved communication with campus units, 2) "Role Information" for new hires in critical positions within the Financial Assistance Clusters to accompany training. | no | Implemented; policy created | Finding 2020-004 Student Financial Assistance Cluster- Special Tests and Provision: Enrollment and Ceritifcation Approval Report
2 | 2020-005 Special Tests and Provisions: COD Reporting | Table B 2020-003 | Recommendation: We recommend the Colleges’ evaluate their procedures and policies around reporting Pell and Direct Loan disbursements to COD to ensure that student information is reported accurately and timely. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to reinforce the process implemented in FY20 to report the COD and drawdown on a weekly basis. The District has experienced continued voids in critical roles and has recently hired 2 Financial Aid Directors at the colleges; two vacancies currently exist. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | yes Item 2019-007 | Plan with Edgerock to Improve Financial Aid Administration | Finding 2020-005 Special Tests and Provisions: COD Reporting
3 | 2020-006 Gramm-Leach Bliley Act | Table B 2020-004 | Recommendation: We recommend that the District engage a third party to perform the risk assessment to address the areas required by the Gramm-Leach-Bliley Act and ensure that there are documented safeguards for identified risks. Explanation of disagreement with audit finding: There is no disagreement with the audit finding. | Action taken in response to finding: Due to COVID the risk assessment was not performed during its usual time as IT was heavily involved with a systemwide upgrade which will utilize PeopleSoft Cloud Security going forward. Documentation of OCI security overview will be provided. | This recommendation will be incorporated as part of the financial module implementation. | no | Implemented - February 2021 w/ Peoplesoft upgrade | Finding 2020-006 Gramm-Leach Bliliy Act
4 | 2020-007 Internal Controls Over Federal Awards | Table B 2020-001 | Recommendation: We recommend that the Colleges’ reinforce their control structure and control environment to ensure there is an appropriate tone at the top of the organization, to monitor proper follow-up on audit findings and review all activity level controls to ensure compliance with the various requirements of the Student Financial Assistance Cluster. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to review practices, reporting expectations, and ensure the separation of duties. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | yes Item 2019-005 and 2019-006 | Plan with Edgerock to Improve Financial Aid Administration | Finding 2020-007 Internal Controls Over Federal Awards
5 | 2020-008 Special Tests and Provisions: Enrollment Reporting | Table B 2020-005 | Recommendation: We recommend the District review its reporting procedures to ensure that enrollment and program information is accurately reported to National Student Loan Data System (NSLDS) as required by regulation. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to review reporting procedures with colleges to ensure enrollment and program date information is accurately reported to NSLDS as required. College Business Services will be included in this process. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | no | Implemented among college offices, weekly meetings with campus financial aid leadership. Utilizing Edgerock for process improvement throughout financial aid processes. Daily meetings with Edgerock are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes. | Finding 2020-008 Special Tests and Provisions: Enrollment Reporting
6 | 2020-009 Outstanding Student Refund Checks | Table B 2020-006 | Recommendation: We recommend the District review its procedures related to outstanding student refund checks to ensure they are being returned to the Department of Education or disbursed to students as stated in the criteria mentioned above. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will review its procedures to ensure that staff is trained to return funds to the Department of Education if payment to student is unsuccessful within a 30-day window. | The District began regular meetings with campus financial aid and business leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting.The District to implement policies to ensure that funds be returned for all unsuccessful student payments within set timeframe (30 days). Campus Business Officers to be involved in the outreach efforts to get funds to students prior to return via COD. | no | Implemented among district/college offices - currently manual communication effort. Currently working with IT support to automate communication to campus offices in support of speed and accuracy. | Finding 2020-010 Outstanding Student Refund Checks
Implemented: utilizing Edgerock for process improvement in this area. Daily meetings with Edgerock and weekly meetings with campus financial aid leadership are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes.
Implemented: utilizing Edgerock for process improvement in this area. Daily meetings with Edgerock and weekly meetings with campus financial aid leadership are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes.